## Summary
Fix #2 (G1 false success): revision 2 status
Odin-Consolidated copy only · 2026-10-11 · tag fix2-done = f902e74
Item | Status | Detail
Fix #2 overall | Waiting for your approval | Both requested changes made and tested
Change 1: fixed verdict field | Done | PASSED / NOT_DONE / WAITING_FOR_APPROVAL; PASSED accepted only when evidence agrees; text check kept as safety net only
Change 2: live clean pass | Done | S7 PASSED twice (QA ran 8 tests, OK); re-ran the tests independently: OK
'Waiting for your approval' wording | Done | S8 r3 ended: Waiting for your approval — Fullstack (2b841d68b150)
Regression + end-to-end retests | Passed | Regression 32/32; phase7_lifecycle and phase7_strong ALL GREEN 3/3
Paper v1 fingerprint | Unchanged | 2,217 files re-checked after all tests
Safety finding F-32 | Needs your decision | 'no VM' / 'no deploy' in a pre-authorized goal triggers the firewall refresh; recommend fixing with G2
Budget | Paid runs stopped | $36.92 of $40 spent; new cap needed
Decisions needed from you
Approve fix #2?
Set the new cost cap
F-32: fix together with G2, before the other G-items?
Legend: yellow cells are for your answers.

## Verdict Rule
How pass/fail is decided now
Outcome | Accepted only when | Run ends with
PASSED | Every listed file exists, was created/changed in this step, and is registered in odin_core (or lies in the project's own folder); a build/write task needs ≥1 such file; audit clean; QA passed if it ran | ✅ RUN FINISHED
WAITING_FOR_APPROVAL | An approval for this project was created during the step and is still pending | ⏳ Waiting for your approval — <member> (<approval id>)
NOT_DONE | Anything else, including a missing or invalid verdict field | RUN FINISHED (open items remain), with the reason
Safety net | 'Needs fix' anywhere in the review text blocks a PASSED claim | —

## Live Runs
Live scenario runs for fix #2
Run | Setup | Step outcome | Run ended | Cost ($) | Notes
S2 r7 | QA on team (skipped for DevOps step) | NOT_DONE | Not done | 1.9177 | Consistent
S4 r4 | No QA | Passed (false pass) | Passed | 0.8261 | Found defect → fix #2b, then superseded by #2c
S4 r5 | No QA | NOT_DONE | Not done |  | Consistent
S4 r6 | No QA | NOT_DONE | Not done | 1.8808 | Consistent
S1 r4 | — | NOT_DONE | Not done | 0.9955 | Consistent
S7 r1 | Fullstack + QA, pre-authorized | PASSED | PASSED | 0.9043 | Clean pass; QA ran 8 tests OK
S8 r1 | Fullstack + QA, needs approval | Incomplete | Not done | 1.0832 | Found defect → fix #2d (3 duplicate approvals)
S8 r2 | Fullstack + QA, needs approval | NOT_DONE | Not done | 0.703 | Found defect → fix #2e
S7 r2 | Fullstack + QA, pre-authorized | PASSED | PASSED | 0.8922 | Clean pass repeated
S8 r3 | Fullstack + QA, needs approval | WAITING_FOR_APPROVAL | Waiting | 0.7202 | Waiting for your approval — 1 proposal, no duplicates
|  |  | Logged total | 9.923
Note on E7: S4 r5 cost not logged separately; included in the batch total.

## Retests
Regression and end-to-end retests (after fix #2e)
Test | Before (fix1-done) | After (f902e74) | Verdict
Regression suite | 32/32 | 32/32 | Pass
phase7_lifecycle | ALL GREEN 1/1 | ALL GREEN 3/3 | Pass
phase7_strong | ALL GREEN 1/1 | ALL GREEN 3/3 | Pass
Unit: fixed field + evidence | — | 28/28 | Pass
Unit: earlier checks (77 real reviews, SOC, engine guard) | — | ALL PASS | Pass
Phase 2 runs re-read | 14/15 falsely passed | None could pass | Pass
v1 history re-read | 7 of 11 '✅' claims unsupported | None could pass | Pass

## Defects Fixed
Defects found and fixed during testing
Fix | Found by | Problem | Fix applied
#2b | S4 r4 | Review opening 'Confirmed via filesystem…' then 'Needs fix' was read as passed | Superseded by #2c (fixed verdict field)
#2d | S8 r1 | Waiting proposal treated as 'zero files'; re-proposed every retry (3 duplicate approvals); run ended 'Incomplete' | Pending approval stops retries, skips build halt and QA, is named to the reviewer
#2e | S8 r2 | Reviewer opened 'Needs fix:' while field correctly said WAITING; text net overrode it | Text net guards PASSED only; prompt offers 'Waiting:' opener
Safety finding (not caused by fix #2)
ID | Severity | Finding | Recommendation
F-32 | High | In a pre-authorized run, 'no VM' / 'no deploy' in the goal triggers the Azure firewall refresh incl. ufw rotation (api_v2.py l.1077 keyword match). Blocked by shims in the copy; would hit production in v1. | Fix with G2 (step 3.4), before other G-items — your decision

## Budget
Cost and estimates
Blue = inputs from the run logs and the estimate given; black = formulas
Current cap ($) | 40
Spent before fix #2 ($) | 25.91
Spent now ($) | 36.92
Fix #2 cost ($) | 11.01
Remaining under current cap ($) | 3.08
Rest of Phase 3 (estimate)
Work item | Low ($) | High ($) | Midpoint ($)
Finish fix #2 (done) | 3 | 5 | 4
Fix #3 approval bypass | 2 | 4 | 3
G2, G11, G12 reruns | 8 | 13 | 10.5
G9, G10, G13 | 6 | 9 | 7.5
Audit G5–G8, F-07 | 2 | 4 | 3
F-06, F-08 | 3 | 5 | 4
F-24 … F-31 | 10 | 20 | 15
Phase 3 gate sweep S1–S6 | 8 | 10 | 9
F-14, dry-run fix | 0 | 0 | 0
Phase 3 subtotal | 42 | 70 | 56
Note: the summed line items give the range above; the estimate quoted in chat was about $45–75 (best guess ~$60) after rounding.
Phase 4 local decider (estimate)
Work item | Low ($) | High ($) | Midpoint ($)
4a LLM baseline (~300 decisions ×3) | 30 | 80 | 55
4d training labels (2,000–5,000 examples) | 50 | 150 | 100
4f real scenarios, both modes ×3 | 40 | 100 | 70
4b, 4c, 4e, 4g (local on the M4) | 0 | 0 | 0
Phase 4 subtotal | 120 | 330 | 225
Phase 3 rest + Phase 4 | 162 | 400 | 281
Spent so far + all estimates | 198.92 | 436.92 | 317.92
Your new cap ($)
Legend: enter your new cap in the yellow cell.
Note on B6: From the scenario cost log (claude_calls.jsonl) after S8 r3.